## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | Shubham |  | Sentiment analysis incorrectly classifies neutral tickets as negative, leading to unnecessary escalations. | Sprint 1 | Single Developer | Functional | Adjusted training dataset and fine-tuned sentiment classification thresholds. | 2025-01-25 | Closed | Resolved with improved dataset.
2 | Shubham |  | Escalation logic based on keyword detection fails to recognize complex urgency indicators. | Sprint 2 | Single Developer | Functional | Proposed implementation of advanced NLP techniques for better phrase understanding | 2025-01-26 | Open | Pending advanced NLP implementation.
3 | Shubham |  | Automated response system generates incomplete replies when encountering uncommon issues. | Sprint 3 | Single Developer | Functional | Working on fallback response mechanisms to improve handling of unknown queries. | 2025-01-27 | Open | Under development.
4 | Shubham |  | Clustering algorithm incorrectly groups unrelated support tickets, affecting issue categorization | Sprint 1 | Single Developer | Algorithmic | Enhanced the clustering model with improved feature extraction. | 2025-01-25 | Closed | Issue resolved with revised logic.
5 | Shubham |  | API integration fails when processing certain edge cases, causing disruptions in workflow automation.. | Sprint 2 | Single Developer | Integration | Strengthened error handling and logging mechanisms for debugging. | 2025-01-26 | Open | Requires additional testing.

## Sheet2
Logical
User Interface
Maintainability
Standards
Others